# Project Charter – Project Ordo

## 1. Project Identification

Project Name: Project Ordo

Project Sponsor: Nestor Wilke, Chief Technology Officer (CTO)

Project Lead: Irvin Sayers

Project Start Date: 15 June 2025

Planned Go-Live Date: 1 March 2027

Charter Approval Date: TBD

## 2. Project Purpose

Project Ordo will deliver a modern enterprise task-tracking solution to replace the legacy TaskStar system. Ordo will become the single system of record for task management, improving usability, integration with Microsoft 365, multilingual accessibility, and future readiness.

## 3. Project Objectives

Replace TaskStar with a configurable Commercial Off-The-Shelf (COTS) solution.

Migrate all existing TaskStar tasks through a one-time data upload.

Ensure Microsoft 365 Copilot integration is fully operational before launch.

Deliver Ordo with English, French, and Spanish support at go-live.

Minimise disruption through structured change management and training.

Fully decommission TaskStar by 1 April 2027.

## 4. Project Scope

In Scope:

Ordo COTS configuration and customisation

One-time TaskStar data migration

Microsoft 365 Copilot integration

Multilingual UI and training (EN/FR/ES)

Change management, communications, and training

Post go-live hypercare

Out of Scope:

Ongoing TaskStar updates after migration

Continuous data synchronisation between systems

Outlook calendar integration at go-live

## 5. Key Milestones

Project Kick-off – 15 June 2025

Core configuration complete – November 2026

UAT complete – December 2026

Copilot integration ready – January 2027

Localisation complete – January 2027

Training ready – February 2027

Ordo go-live – 1 March 2027

TaskStar decommissioned – 1 April 2027

## 6. Budget Summary

Total Approved Budget: CAD 4,015,000

The budget includes licensing, implementation, Copilot integration, localisation, change management, security and compliance, project management, and contingency.

## 7. Governance and Roles

Nestor Wilke – Project Sponsor (CTO)

Irvin Sayers – Project Lead

Diego Siciliani – Change Management & Business Readiness

Lidia Holloway – Product Management & Requirements

Allan Deyoung – Information Security & Privacy

## 8. Success Criteria

90% of active users adopt Ordo within three months of go-live.

All TaskStar data available post-migration.

Microsoft 365 Copilot usable at launch.

Ordo available in English, French, and Spanish on day one.

TaskStar retired without disruption.

## 9. Approval

This charter authorises Project Ordo to proceed as defined.

Project Sponsor Signature: ______________________   Date: __________

Project Lead Signature: ________________________   Date: __________