## Slide 1
PROJECT ORDO
Introducing Your New Task Management Platform
Replacing TaskStar · Go-Live: 1 March 2027
Total Approved Budget: CAD $4,015,000

## Slide 2
Why Ordo?
Project Ordo will deliver a modern enterprise task-tracking solution to replace the legacy TaskStar system — becoming the single system of record for task management across the organization.
Configurable COTS
A modern, off-the-shelf platform customized to our organizational needs
Multilingual
Full support for English, French, and Spanish at launch
M365 Copilot Ready
Deep integration with Microsoft 365 Copilot for AI-powered task management
Seamless Migration
One-time data migration from TaskStar with zero data loss

## Slide 3
What's Changing
TaskStar is being retired. Here's what you need to know about the transition.
TaskStar
Freezes
Feb 2027
Data
Migration
Feb 2027
Ordo
Go-Live
1 Mar 2027
Hypercare
Period
Mar–Apr 2027
TaskStar
Retired
1 May 2027
TaskStar will stop accepting new entries after the one-time data migration
TaskStar remains read-only until 1 May 2027 for reference
All existing tasks will be available in Ordo post-migration

## Slide 4
Key Milestones
Jun 2025
Project Kick-off
Nov 2026
Core Configuration Complete
Dec 2026
User Acceptance Testing Complete
Jan 2027
Copilot Integration & Localization Ready
Feb 2027
Training Materials Ready (EN/FR/ES)
1 Mar 2027
Ordo Go-Live
1 Apr 2027
TaskStar Decommissioned
Outlook Calendar Integration planned for Q3 2027 as a future enhancement

## Slide 5
Budget Overview
Total Approved Budget: CAD $4,015,000
Chart: 
| Project Management | COTS Licence | Custom Extensions | Core Configuration | Copilot (Design + Build) | COTS Support | Data Mapping + Migration | Localisation | Training Design | Security & Compliance
Budget | 760 | 650 | 485 | 480 | 415 | 300 | 205 | 205 | 100 | 95
Project Management
$760K
COTS Licence
$650K
Custom Extensions
$485K
Core Configuration
$480K
Copilot (Design + Build)
$415K
COTS Support
$300K
Data Mapping + Migration
$205K
Localisation
$205K
Training Design
$100K
Security & Compliance
$95K

## Slide 6
Monthly Spend Profile
CAD thousands — July 2025 through April 2027
Chart: 
| Jul 25 | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27
Monthly Spend (CAD K) | 70 | 80 | 75 | 75 | 80 | 70 | 170 | 175 | 205 | 205 | 165 | 165 | 180 | 190 | 830 | 150 | 145 | 105 | 115 | 265 | 100 | 80
COTS Licence
acquisition

## Slide 7
Your Project Team
Irvin Sayers
Project Lead
Drives day-to-day project delivery and coordination
Nestor Wilke
CTO & Sponsor
Executive sponsor accountable for strategic decisions
Diego Siciliani
Change Management
Leads business readiness, communications, and training
Lidia Holloway
Product Management
Manages requirements and product configuration
Allan Deyoung
Security & Privacy
Oversees information security and compliance

## Slide 8
Key Risks & Mitigations
User Resistance to Change
Early communication campaigns and multilingual training materials across English, French, and Spanish
Data Migration Issues
Validated test migrations planned before the February 2027 production cutover
Copilot Integration Delays
Prioritized as a non-negotiable delivery — dedicated team and early design phase
Incomplete Localization
Language scope locked early with validation checkpoints before go-live

## Slide 9
What Success Looks Like
90%
of active users adopt Ordo within 3 months of go-live
100%
of TaskStar data available post-migration
Day 1
Microsoft 365 Copilot usable at launch
3 Languages
English, French, and Spanish on day one
Zero
business disruption during TaskStar retirement

## Slide 10
Get Ready for Ordo
A simpler, smarter way to manage your tasks — launching 1 March 2027
Questions? Reach out to the Project Ordo team
Project Lead: Irvin Sayers · Sponsor: Nestor Wilke (CTO)