# Project Ordo

## Overview

Ordo is a new enterprise task‑tracking solution scheduled for organisation‑wide roll‑out on 1 March 2027. Ordo will replace the existing system, TaskStar, and become the single system of record for task management.

Project kick‑off took place on 15 June 2025.

## Transition from TaskStar

- TaskStar will stop accepting new or modified entries after the one‑time data migration.

- Existing TaskStar tasks will be uploaded once into Ordo in February 2027 (exact date to be confirmed).

- TaskStar will remain read‑only until 1 May 2027.

- After 1 May 2027, TaskStar will be fully decommissioned.

## Solution Scope

- Ordo is a Commercial Off‑The‑Shelf (COTS) product customised to organisational needs.

- Core task tracking and reporting features available at go‑live.

- Microsoft 365 Copilot integration is mandatory and must be fully functional before roll‑out.

- The Ordo user interface, notifications, and training materials must be fully localised in English, French, and Spanish at launch.

- Outlook calendar integration is planned as a later enhancement.

## Key Deliverables & Target Dates

| Deliverable | Target Date |
| --- | --- |
| Project Kick‑off | 15 June 2025 |
| Core Ordo configuration complete | November 2026 |
| User Acceptance Testing (UAT) complete | December 2026 |
| Copilot integration ready | January 2027 |
| Language localisation (FR & ES) complete | January 2027 |
| Training materials & support content ready (EN/FR/ES) | February 2027 |
| TaskStar data migration | February 2027 (TBC) |
| Ordo go‑live | 1 March 2027 |
| Hypercare & stabilisation period | March–April 2027 |
| Outlook integration (optional) | Q3 2027 |
| TaskStar decommissioned | 1 May 2027 |

## Project Team

- Irvin Sayers – Project Lead

- Nestor Wilke – CTO, Project Sponsor

- Diego Siciliani – HR, Change Management & Business Readiness

- Lidia Holloway – Product Management & Requirements Lead

- Allan Deyoung – Information Security & Privacy Lead

## RACI

| Activity | Irvin Sayers | Nestor Wilke | Diego Siciliani |
| --- | --- | --- | --- |
| Project delivery | R | A | C |
| Technical decisions | C | A/R | C |
| Change, communications & localisation readiness | C | A | R |
| Training & adoption (EN/FR/ES) | C | A | R |

R = Responsible, A = Accountable, C = Consulted

## Key Risks

- User resistance to change → Mitigated through early communication and multilingual training materials.

- Data migration issues → Validated test migrations before February 2027.

- Copilot integration delays → Prioritised as a non‑negotiable delivery.

- Incomplete localisation → Locked language scope and validation before go‑live.

## Success Metrics

- ≥ 90% of active users using Ordo within 3 months of go‑live.

- All TaskStar data successfully available in Ordo post‑migration.

- Microsoft 365 Copilot usable for task creation and insights at launch.

- Ordo available in English, French, and Spanish on day one.

- TaskStar fully retired with no business disruption.

## Summary

Project Ordo modernises task management through a configurable COTS platform, deep Microsoft 365 integration, multilingual readiness, and a structured transition away from TaskStar. The project prioritises adoption, accessibility, and future‑ready capabilities while minimising disruption to employees.